## Bug -MyBzB
Module | Request | API | Bug Description | Test Status | Pending Functionality | Expected Result | Issue Proof | Status |  | Pending API
Disable - Customer | GET | {{url}}api/v1/admin/disabled-customer/12 | In Disable customer API while hit the API than 404 not found error is displayed Instead of that " Record not found " validation needs to apply | FAIL | Validation needs to set instead of "404 not found " | Validation needs to set instead of "404 not found " | https://drive.google.com/file/d/1ia5YP8He3Houi9bZzTxXgeRrlsRRABSA/view?usp=drive_link | done | Needs to Confirm | Order Listing API
Product cart List Product List Wishlist list | GET | http://18.212.173.237/images/product/17/133005.jpg | Product Image didn't display while hit the API Product Cart List, Wishlist list API | FAIL | Missing to display Product Image while run api | Product list and cart list api product image not displayed | https://drive.google.com/file/d/1oH6EGmbIurKeEuPuJAsjg13lwod4u-t9/view?usp=drive_link | please check with seller website
User default address | POST | {{url}}api/v1/set_user_address_default | Issue to change the default address {{url}}api/v1/set_user_address_default while user check address default address than in user address list default address value should be displayed as 1 | FAIL |  | Issue to change the default address {{url}}api/v1/set_user_address_default while user check address default address than in user address list default address value should be displayed as 1 | https://drive.google.com/file/d/1d2fUtZGXEtKdFkGDMyePGRoA_4OSfcSH/view?usp=drive_link
User default address | POST | {{url}}api/v1/set_user_address_default | When run the api -> {{url}}api/v1/set_user_address_default than internal server error is displayed | FAIL |  | When run the api -> {{url}}api/v1/set_user_address_default than internal server error is displayed | https://drive.google.com/file/d/1CVXYZ6sFJ5K-zjyA3C6O9cs7yfFJt75F/view?usp=drive_link
User update address | POST | {{url}}api/v1/update_user_address | When run the api -> {{url}}api/v1/update_user_address than internal server error displayed | FAIL |  | When run the api -> {{url}}api/v1/update_user_address than internal server error displayed | https://drive.google.com/file/d/1-Gp6M0K5vMoMrigHfXjCzpIHqAQN8Tne/view?usp=drive_link
List Review Ratings | POST | {{url}}api/v1/list_ratings_review | Due to User profile update api Pending , list_ratings_review api is reflecting below error ""Attempt to read property \"user_id\" on null" | FAIL | User profile update api needs to ready | Once user profile update api developed than list_ratings_review api should be working as expected and rating list should be display | https://drive.google.com/file/d/1SH2b47My_USKQ_Zba3MvhwanYP-fKcSw/view?usp=drive_link
List Review Ratings | POST | {{url}}api/v1/list_ratings_review | When hit the list rating review api without upload images than previous image captured in response and displayed | FAIL |  | Image should display exactly what user upload the images, old images should not trail gate when user not upload the image | https://drive.google.com/file/d/1As6imawSnJNeIyyLJppliYosz1g6Vj7z/view?usp=drive_link
Update_profile | POST | {{url}}api/v1/update_profile | Customer side in Profile update api success message "Record fetch successully" should be displayed as "Profile updated successfully" | FAIL |  | Customer side in Profile update api success message "Record fetch successully" should be displayed as "Profile updated successfully" | https://drive.google.com/file/d/1B1A04DHIyxdwaTUg_w6lTufR2sT3ejnE/view?usp=drive_link
Update_profile | POST | {{url}}api/v1/update_profile | In Update Profile - When Keep blank email and hit api than validation displayed as "Email is already exists" it should be like "Please enter the email address" | FAIL |  |  | https://drive.google.com/file/d/1_2FgaezeUCVY8DbDXMnxqd1NSyoGGuQw/view?usp=drive_link | its not issue ,its functionality
Add-user-address | POST | {{url}}api/v1/add_user_address | In Add-user-address api as per the developer requirement needs to pass Id's of City, State and Country | FAIL |  |  | https://drive.google.com/file/d/13KAPXeSw-W2cqrtVEBJlY4bKRI4S4cU4/view?usp=drive_link | need discussion | As per developer it will required
List State List City | POST | {{url}}api/v1/list_city {{url}}api/v1/list_state | In List City and List State When Record not found than it should be displayed with Array Object [] instead of {} curly bracket | FAIL |  |  | https://drive.google.com/file/d/1B4BEKLZgva0NNvzBWDXVwHATnqyqYMtR/view?usp=drive_link https://drive.google.com/file/d/1J07ERGB4go_kb-rrgELWU9IT082reFTX/view?usp=drive_link | working properly | Still Issue is facing
Seller-List | GET | {{url}}api/v1/seller_list | Seller List Get API should be Post API and User should able to Enter Page no. For Pagination list | FAIL |  |  | https://drive.google.com/file/d/1iK8syUA_0UDpy9z0j4C_CHboExV4bylH/view?usp=drive_link
Place_order_details | POST | {{url}}api/v1/place_order_details | In Place_Order_Details API while hit the API than image is not displayed | FAIL |  |  | https://drive.google.com/file/d/1UNf9sXFoeAWI3GisEfqdSlDpqwrGRsGk/view?usp=drive_link
Place_Order_Cancel | POST | {{url}}api/v1/place_order_cancel | After Cancelled the Order , Cancelled status not displayed in Place Order List | FAIL |  |  | https://drive.google.com/file/d/1UIO82AKjRu8IQ7GRZ7sivpUjMmO2pONf/view?usp=drive_link
Product_list_cart_item | POST | {{url}}api/v1/product_list_cart_item | In Product List -Cart Item Image is displayed as " " Empty , Product image should displayed | FAIL |  |  | https://drive.google.com/file/d/1WTzYaJRA1Gle-wRGZBWBs03uipG8zQX8/view?usp=drive_link
Place_order_list | POST | {{url}}api/v1/place_order_list | Order ID needs to Generate as Separate for Each Order for e.g. For Jhumkha 2 Qty has been Placed , for both two separate Order needs to Generate In Order_id "Order#" no needs to display Only Numeric Order id needs to display In Order Status instead of String Pending, Shipped, Delivered , Order status needs to display in ID like 1, 2, 3, etc. for e.g. pending =1, cancelled =2 , etc. | FAIL |  |  | https://drive.google.com/file/d/1RjnCkAyBKz2KZPpV-tovqJrc_Qqh1FnO/view?usp=drive_link
Place_order_details | POST | {{url}}api/v1/place_order_details | Missing Order Status, Delivery Address, Order Summary, Payment Information and Delivery Instructions in API | FAIL |  | {{url}}api/v1/place_order_details response fields needs to include Order Summary, Delivery Address, etc. fields which given in figma | https://drive.google.com/file/d/1fByggqzX0-6vtKPrrDGvc3_qwMg8SJVe/view?usp=drive_link
Sendotp | POST | {{url}}api/v1/sendotp | In SendOTP API - Validations are missing as below - In Phone number while entered String value than SQL error is reflecting - When Country code missing than validation needs to set - In Country code when entered String value than Validation needs to set | FAIL | For SendOTP Validations are pending to apply | On Invalid value in Send OTP validations needs to set | https://drive.google.com/file/d/14uDrUqCoNCDAZ9ogEjlgYBYYxt-1pO1l/view?usp=drive_link https://drive.google.com/file/d/164eenfgDin9ySlcl2fuiU3UZ5UutAz_x/view?usp=drive_link https://drive.google.com/file/d/1uSkXksDKOZskk3wU4C0ZA0v6miw8HMoI/view?usp=drive_link | done | In Country code still user able to entered string value
Add_Review_Ratings | POST | {{url}}api/v1/add_review_ratings | In {{url}}api/v1/add_review_ratings api when user entered invalid Order Id than validation should be display like " Order ID is incorrect please entered correct Order ID " | FAIL | Validation needs to set for add_review_ratings | Validation should be set when user entered invalid order id | https://drive.google.com/file/d/1SqRbhvl--6kDe3VbXaq9dPSsFThVpTZ3/view?usp=drive_link | done
List_ratings_review | POST | {{url}}api/v1/list_ratings_review | After Add the Ratings for products while run the API for {{url}}api/v1/list_ratings_review with correct product ID than "Attempt to read property \"user_id\" on null", error is coming | FAIL | Rating review list product should be displayed | Rating review list product should be displayed instead of error | https://drive.google.com/file/d/1cGh5EVozlIKr_B8LX-Dz-VKuKRGPPQSH/view?usp=drive_link | done-user profile not created that’s why error coming,please testing end to end
List_Wishlist | POST | {{url}}api/v1/list_wishlist | While hit the product image api to display the product image than wishlist image is not displayed | FAIL |  | While hit the product image api to display the product image than wishlist image is not displayed | https://drive.google.com/file/d/106JET8fO9s9o3Goa-KoG0--ne6EaHok7/view?usp=drive_link | Please check from vendor ui
Product_details | POST | {{url}}api/v1/product_details | In product details api when entered product id till 34 it is displayed response but after product id 34 it is giving an error as "Something went wrong" | FAIL | "Something went wrong" error needs to resolved | "Something went wrong" error needs to resolved | https://drive.google.com/file/d/1BiIV0ZXygbr961EEIIchr7KerVWb1vvt/view?usp=drive_link | Please check from vendor ui
Product_details | POST | {{url}}api/v1/product_details | After fetching product details when run API of product details than some product images getting and some product image giving an error | FAIL | Image displayed issue in product details | In Product detail when run api of product image than all images should display | https://drive.google.com/file/d/1zy09tJ02wZZY_o9FdrI8zCSCMC8Y2pPL/view?usp=drive_link | Please check from vendor ui
Seller-Enable-Disable-Product | POST | {{url}}api/v1/seller/enable-disable-product | Deactived product is display in product list , once product status change as deactive from seller than that product should not display in Product list, Similar Item, Wishlist, Cart |  | After Deactivated the product still product is displayed in Product List, Homepage , which needs to fix

## API Success Status
Super Admin Side - My BzB |  |  | Customer side | Status | Date | BUG in API | Short Description of Bug |  | Date
API Path | Status | Date | {{url}}api/v1/general_settings-app-data | PASS | 2024-05-21 | {{url}}api/v1/update_user_address | Internal Server Error | Customer side | 2024-05-24 | Out of Scope currently or Pending
{{url}}api/v1/admin/login | PASS | 2024-05-21 | {{url}}api/v1/admin/list-product-occasion | PASS | 2024-05-21 | {{url}}api/v1/set_user_address_default | Internal Server Error | Customer side | 2024-05-24 | {{url}}api/v1/admin/add-product-size
{{url}}api/v1/admin/update-general-settings | PASS | 2024-05-21 | {{url}}api/v1/sendotp | PASS | 2024-05-21 | {{url}}api/v1/admin/get-customer-list | Mismatch with Figma - Customer Name, mobile number, etc. not displayed | Admin Side | 2024-05-24 | {{url}}api/v1/admin/add-product-weight
{{url}}api/v1/admin/list-general-settings | PASS | 2024-05-21 | {{url}}api/v1/verifyotp | PASS | 2024-05-21 | {{url}}api/v1/admin/disabled-customer/ | Displayed errors while run the api | Admin Side | 2024-05-24 | {{url}}api/v1/admin/enable-disable-color
|  |  | {{url}}api/v1/add_wishlist | PASS | 2024-05-22 | {{url}}api/v1/admin/disabled-seller/17 | Displayed errors while run the api | Admin Side | 2024-05-24 | {{url}}api/v1/admin/seller_enquiry_list
Occasion |  |  | {{url}}api/v1/remove_wishlist | PASS | 2024-05-22 |  | Seller Register API reflect the error as "Something went wrong" | Seller Side | 2024-05-24
{{url}}api/v1/admin/add-product-occasion | PASS | 2024-05-21 | {{url}}api/v1/list_wishlist | PASS | 2024-05-22
{{url}}api/v1/admin/enable-disable-occasion | PASS | 2024-05-21
{{url}}api/v1/admin/delete-product-occasion | PASS | 2024-05-21 | {{url}}api/v1/add_user_address | PASS | 2024-05-24
{{url}}api/v1/admin/list-product-occasion | PASS | 2024-05-22 | {{url}}api/v1/delete_user_address | PASS | 2024-05-24
|  |  | {{url}}api/v1/list_user_address | PASS | 2024-05-24
Category
Note :- Currently observed that authorization is missing in multiple api's - Authorization needs to set across all required api's
{{url}}api/v1/admin/enable-disable-category | PASS | 2024-05-21 | {{url}}api/v1/product_add_to_cart | PASS | 2024-05-22
{{url}}api/v1/admin/list-category/ | PASS | 2024-05-21 | {{url}}api/v1/product_update_to_cart | PASS | 2024-05-22
{{url}}api/v1/admin/delete-category | PASS | 2024-05-21 | {{url}}api/v1/product_delete_to_cart | PASS | 2024-05-22
{{url}}api/v1/admin/edit-category | PASS | 2024-05-21 | {{url}}api/v1/product_list_cart_item | PASS | 2024-05-22
Metal | [5 empty] | Seller Side
{{url}}api/v1/admin/add-product-metal | PASS | 2024-05-21 | {{url}}api/v1/list_state | PASS | 2024-05-22 | {{url}}api/v1/seller/delete-product
{{url}}api/v1/admin/update-product-metal | PASS | 2024-05-21 | {{url}}api/v1/list_country | PASS | 2024-05-22
{{url}}api/v1/admin/edit-product-metal | PASS | 2024-05-21 | {{url}}api/v1/list_city | PASS | 2024-05-22
{{url}}api/v1/admin/list-product-metal | PASS | 2024-05-21
{{url}}api/v1/admin/delete-product-metal | PASS | 2024-05-21 | {{url}}api/v1/get_profile | PASS | 2024-05-27
Promotional |  |  | {{url}}api/v1/logout | PASS | 2024-05-30
{{url}}api/v1/admin/update-promotional-products | PASS | 2024-05-21
{{url}}api/v1/admin/list-promotional-products | PASS | 2024-05-21
{{url}}api/v1/admin/delete-promotional-products | PASS | 2024-05-21
{{url}}api/v1/admin/add-promotional-products | PASS | 2024-05-21
General Settings
{{url}}api/v1/admin/update-general-settings | PASS | 2024-05-21
{{url}}api/v1/admin/list-general-settings | PASS | 2024-05-21
{{url}}api/v1/admin/seller_list | PASS | 2024-05-21
Color
{{url}}api/v1/admin/add-product-color | PASS | 2024-05-21
{{url}}api/v1/admin/list-product-color | PASS | 2024-05-21
{{url}}api/v1/admin/enable-disable-color | PASS | 2024-05-21
{{url}}api/v1/admin/update-product-color | PASS | 2024-05-21
{{url}}api/v1/admin/delete-product-color | PASS | 2024-05-21
Banner
{{url}}api/v1/admin/list-customer-banner | PASS | 2024-05-21
{{url}}api/v1/admin/update-customer-banner | PASS | 2024-05-21
{{url}}api/v1/admin/delete-customer-banner | PASS | 2024-05-21
{{url}}api/v1/admin/add-customer-banner | PASS | 2024-05-21
{{url}}api/v1/admin/logout | PASS | 2024-05-30

## MyBzB (hidden)
Bug Report - Headway
Bug ID | Bug Status | Bug Description | Date | Bug Type | Bug Reproduce Step | Priority | Issue Proof | Device/Browser | Developer Name | Developer Comments | Tester Comment
5 | Open | In Seller Side Add Products detail request and response fields needs to set as per the document , currently mismatch and missing below fields Request :- User ID, By Search Name, Brand Name, Category, Category_ID, FilterBy, SortBy Response :- Product Image, Rating, total rating, Is Favorite, Seller Name | 2024-05-03 | API
6 | Open | In Seller side Add Products API validations needs to set for Blank product name, price, etc. fields | 2024-05-03 | API
SuperAdmin API
001 | Open | In SuperAdmin - Get Profile Needs to make changes as when Send API request for invalid user "Record successfully fetch" message getting displayed | 2024-05-08 | API |  |  | https://drive.google.com/file/d/1JwSqaUXbm7_uyP0qmb1woTrR4i1k0Dll/view?usp=drive_link
002 | Open | Forgot Password, Reset Password, Dashboard API not found Superadmin side | 2024-05-08 | API
003 | Open | Missing Login API superadmin side | 2024-05-08 | API
004 | Open | Seller List/Vendor List API needs to developed as per the figma design for admin currently developed API field for Seller List fields are mismatch | 2024-05-08 | API |  |  | https://drive.google.com/file/d/1BcJG3t2txPPBSe9IxQLU-mMglhz4kxfh/view?usp=drive_link
005 | Open | Disable Customer API found Incomplete as Validations for invalid value of customer when send API it displayed as success instead of validation error like "Customer not found" Request and response Mismatch with document | 2024-05-08 | API
006 | Open | For Category List - - Authorization missing and Common param not found | 2024-05-08 | API
007 | Open | In Add Categories - as per the Figma design There is Name, Size, Status but in current API Add Categories found Name, Image only as well while send API than { "status": false, "message": "Undefined array key \"image\"", "data": {} } this error is coming | 2024-05-08 | API |  |  | https://drive.google.com/file/d/1Ys1M-W3utijhqkDnpsPjf1MfMv1k8kke/view?usp=drive_link
008 | Open | In Edit Categories as per the Figma there is fields like Name, Size, Status Which mismatch with SuperAdmin Edit Categories API's as there are fields in request body like Name, Image and User also get edit success message for incorrect edit -category | 2024-05-08 | API |  |  | https://drive.google.com/file/d/1BY24acCRXHF2XM8HQ5BSGAgWsf66qbHF/view?usp=drive_link
009 | Open | list-product-size API's mismatch with figma like " Product name " | 2024-05-08 | API |  |  | https://drive.google.com/file/d/1vPbRc2Ood_fUBYucEttI7EJdwlTrZF1a/view?usp=drive_link
010 | Open | While send add-product - size API request than in response received response as below "message": "SQLSTATE[42S22]: Column not found: 1054 Unknown column 'category_id' in 'field list' (Connection: mysql, SQL: insert into `product_sizes` (`category_id`, `size`, `value`, `updated_at`, `created_at`) values (1, mm, 16.70, 2024-05-08 07:06:54, 2024-05-08 07:06:54))", | 2024-05-08 | API |  |  | https://drive.google.com/file/d/16gZysi0JTEYQ1gMC1e1l3GZ9UO9krZUq/view?usp=drive_link
011 | Open | In Edit Product Size When user entered incorrect value than also success message is getting pop-up there should be validation like "Product not found" | 2024-05-08 | API |  |  | https://drive.google.com/file/d/117s2Nea27xz59v5Vi-qSMbcqesYKM0Mt/view?usp=drive_link
012 | Open | On Invalid Value while send "delete-product-metal" Success Message is getting displayed Instead of that "Product not found" validation needs to apply | 2024-05-08 | API |  |  | https://drive.google.com/file/d/1O-p6A_JCHZCjzaItwJDlQkYolN6TntPF/view?usp=drive_link
Customer Side
001 | Open | While User Entered Wrong OTP "api/v1/verifyotp" than "Undefined variable $token" is getting displayed Instead of that "Please enter valid OTP" should be display | 2024-05-09 | API |  |  | https://drive.google.com/file/d/1pyW7w5VBoEPW3LYZR_f_QUKu45HhMWzz/view?usp=drive_link
002 | Open | Contact Us Customer Side While Send API than Internal Server Error is getting Displayed | 2024-05-09 | API |  |  | https://drive.google.com/file/d/15oIIHpgfppdBIjGYj_1Qig2H4uq_la6M/view?usp=drive_link
003 | Open | Customer side - In Verify OTP common fields are missing in response like First Name, Last Name, Email and Profile Photo | 2024-05-09 | API |  |  | https://drive.google.com/file/d/1bQk81PR-Gab5TYZv8n4AIzo_lAmF2FM_/view?usp=drive_link
API Superadmin Test - Note :- Add Product still testing pending , Occassions done, Purity and metal testing will test again once api changes implement
001 | Open | Add-Category and Update Category - request field in size field when user pass string than validation needs to set | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1SMe-h9dwux2cf4n1nh8ZQsFo38lb5JV0/view?usp=drive_link https://drive.google.com/file/d/1JXNuZ5f9XavC_aFtWVS0lq9F04M1iNYr/view?usp=drive_link
003 | Open | Metal Product API, Add, update, delete, edit error is displaying while run it | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1WkQXYmeZ_Xm6dAdaa98iPCf6MnGiGuj1/view?usp=drive_link
004 | Open | In update product occasion change the status as deactive and run the api than status is unable to change as deactive | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1DkQF1RfnczTODMZPNTkaTCRu5FsiqTua/view?usp=drive_link
005 | Open | UTC format is needs to apply for all request and response which is missing | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1HuRqrpshIhBw0i79W4Almh8r1OJewkKz/view?usp=drive_link
006 | Open | In List product purity API in response "Empty" value should set instead of "Null" | 2024-05-14 | API |  |  | https://drive.google.com/file/d/13SmOAVs9v1YWnKQkc3rLDYYGSQbFL49p/view?usp=drive_link
007 | Open | In Add Product API While Run the API, than Images of products is not displayed in response | 2024-05-15 | API |  |  | https://drive.google.com/file/d/1OKHC05TSnt62Nl1u-Uj_UIGBdlNjYgK4/view?usp=drive_link
008 | Open | In Add Product API Validation for Images missing | 2024-05-15 | API |  |  | https://drive.google.com/file/d/1CUfih25ukDXB9-7b1tqd6dZnHFKKtLah/view?usp=drive_link
009 | Open | In Add Product for Gem Stones validations needs to apply like diamond carat, diamond clarity, diamond shape, etc. | 2024-05-15 | API |  |  | https://drive.google.com/file/d/1zx7Yt3BhZzRki6kMFOveNlTYPmpc18Em/view?usp=drive_link
010 | Open | In Add product authorization needs to apply which is missing | 2024-05-15 | API |  |  | https://drive.google.com/file/d/1u-_0ikbLKCQT9RdxuvjOwOBln2EoG8J6/view?usp=drive_link
011 | Open | In Add Product Validations needs to apply for minimum and maximum images file size as 200 kb is max size, as well maximum 5 images are allowed to upload as per the figma | 2024-05-15 | API |  |  | https://drive.google.com/file/d/1IpeYxfPkS0ukUW4qlFd692n5Wt1bBkLJ/view?usp=drive_link
| Open | In Purity activate and deactive api is pending yet to implement | 2024-05-15 | API |  |  | https://drive.google.com/file/d/1S6mB_mMdNh971LiYjQd_FwEDHmuz3FHm/view?usp=drive_link

## Other Issue Pending
Bug Report - Headway
Bug ID | Bug Status | Bug Description | Date | Bug Type | Bug Reproduce Step | Priority | Issue Proof | Device/Browser | Developer Name | Developer Comments | Tester Comment
| Open | Add-Category and Update Category - request field in size field when user pass string than validation needs to set | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1SMe-h9dwux2cf4n1nh8ZQsFo38lb5JV0/view?usp=drive_link https://drive.google.com/file/d/1JXNuZ5f9XavC_aFtWVS0lq9F04M1iNYr/view?usp=drive_link
| Open | In update product occasion change the status as deactive and run the api than status is unable to change as deactive | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1DkQF1RfnczTODMZPNTkaTCRu5FsiqTua/view?usp=drive_link
| Open | UTC format is needs to apply for all request and response which is missing | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1HuRqrpshIhBw0i79W4Almh8r1OJewkKz/view?usp=drive_link
| Open | In List product purity API in response "Empty" value should set instead of "Null" | 2024-05-14 | API |  |  | https://drive.google.com/file/d/13SmOAVs9v1YWnKQkc3rLDYYGSQbFL49p/view?usp=drive_link
| Open | In add-category validations needs to set as per the figma specification like Max Image Size should be 200KB, max 150px * 150px image resolutions is valid , currently validations are missing | 2024-05-16 | API |  |  | https://drive.google.com/file/d/16Gi8UR29H3T8NpzHUgZdHQAo71o30n0b/view?usp=drive_link https://drive.google.com/file/d/1VSUYyAlzdMw1CY1PzHXI23Oh4_TnVtdI/view?usp=drive_link
| Open | Seller Register API reflect the error as "Something went wrong" | 2024-05-16 | API |  |  | https://drive.google.com/file/d/1We7EFOBz2rBm7oohbiTHirxPmIhxHjLL/view?usp=drive_link
| Open | {{url}}api/v1/seller/add-product - In Add product API currently SKU ID is not auto generated, SKU ID should be auto generated Note : - Not a bug needs to make understand | 2024-05-24 | API |  |  | https://drive.google.com/file/d/1iH4uMTbRUhSWgbu5g6ecm5p-acy_w6K8/view?usp=drive_link

## Resolved
008 | "Register a new membership" needs to remove from Login page | 2024-05-09 | Admin side issue | "Register a new membership" needs to remove from Login page | "Register a new membership" needs to remove from Login page | Medium | https://drive.google.com/file/d/1kR584nEs3JDTP3xcxASHYiVTtozCcxwQ/view?usp=drive_link |  | Rakesh Singh | Open
3 | Open | In Product list API Request and Response while compare with document below fields are missing Request :- User ID, By Search Name, Brand Name, Category, Category_ID, FilterBy, SortBy Response :- Product Image, Rating, total rating, Is Favorite, Seller Name | 2024-05-03 | API
4 | Open | Discount value displayed as "null" should be " " (Empty) in Product list API | 2024-05-03 | API
002 | Open | In Delete Category When User entered wrong ID or not exist data than validation needs to set | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1230awdPeuF0qdvLcU2JqLe3SOqCYmI-K/view?usp=drive_link
012 | Open | In List Product metal API - {{url}}api/v1/admin/list-product-metal status and date (Date mentioned in improper format) are missing | 2024-05-16 | API |  |  | https://drive.google.com/file/d/1aIgYsDXE5bpeMnvDKhMFnGHadoPRdsVS/view?usp=drive_link
015 | Open | As per figma user can update multiple purity type, but while update multiple purity type from api , validation error displayed Note :- Change the requirement so not consider as an bug | 2024-05-16 | API |  |  | https://drive.google.com/file/d/1lccs2fCDAdBEVs3EF6KYjMPirCtRpdOk/view?usp=drive_link
Add - Wishlist API | POST | {{url}}api/v1/add_wishlist | Pagination missing in wishlist API |  | FAIL | Needs to add pagination as per document | Needs to add pagination as per document | https://drive.google.com/file/d/1kH5u7bS-Tna0Hb9__jAPdNx4H0_Ah_26/view?usp=drive_link
Product Detail | POST | {{url}}api/v1/product_details | When Add product with Gemstone active than Gemstone detail needs to display in Product detail like Diamond shape, Clarity, etc. | Figma | FAIL | Missing to display Gemstone detail in Product detail | When Add product with Gemstone active than Gemstone detail needs to display in Product detail like Diamond shape, Clarity, etc. | https://drive.google.com/file/d/1MxGtBm5znPr7oiKCxbOnMk6pDCn68ydI/view?usp=drive_link |  |  | Products List
List Product Purity | GET | {{url}}api/v1/admin/list-product-purity Resolved | "Attempt to read property \"name\" on null", display this error while hit the API |  | FAIL | Error needs to resolved | Purity list should be display | https://drive.google.com/file/d/1Ox4WNtJhVuuIO1jgZ60dreyP3zvQJ33t/view?usp=drive_link | Resolved |  | Customer Detail API
Login - Email | POST | {{url}}api/v1/admin/login | While entered wrong email address like - headwaybusinesssolutions1@gmail.com than server error is coming Instead of that validations needs to apply | headwaybusinesssolutions1@gmail.com - Wrong Email | FAIL | Validation needs to set | Validation needs to apply as "Please Entered Correct Email address" | https://drive.google.com/file/d/1Ofpc26HgJdkg4lG9F9j2vgvZfPiVHt-e/view?usp=drive_link | Resolved |  | Forgot Password
Login - Password | POST | {{url}}api/v1/admin/login | On Wrong Password Admin Login Successfully | 1 | FAIL | Eye icon pending to apply to show Password | Validation needs to apply as "Please entered Correct Password" | https://drive.google.com/file/d/1Evj3peGEk_mETweO0-2OgV1SpTLAN4M3/view?usp=drive_link | Resolved |  | Dashboard
List Product Occasion | GET | {{url}}api/v1/admin/list-product-occasion | In List Product Occasion date format is given as "2024-05-14T11:37:17.000000Z", which needs to change in redable format | Figma | FAIL | Date format needs to change | In List Product Occasion date format is given as "2024-05-14T11:37:17.000000Z", which needs to change in redable format | https://drive.google.com/file/d/1A4RY2VP3S_DZyvtI2Z7pGP97gn492aXV/view?usp=drive_link
Wishlist List | POST | {{url}}api/v1/list_wishlist | In Wishlist API when Empty than currently it is displayed as object [] which needs to change as an array | FAIL | [] array object should be {} bracket for empty value | [] array object should be {} bracket for empty value | https://drive.google.com/file/d/1o6VL89frIQCZIlTQNmIJANgEkKOqkEb3/view?usp=drive_link
Store | GET | {{url}}api/v1/admin/seller_list | Seller List API Mismatch With Figma like Owner Name, Phone number, City, etc. not present in API Response | Figma | FAIL | Owner Name, Phone number, City, etc. |  | https://drive.google.com/file/d/1o3GwSKPW03tzlP7s-Rvs-VlKuzuO63aQ/view?usp=drive_link |  |  | ADD Store/ Add Seller
Seller Enquiry list | GET | {{url}}api/v1/admin/seller_enquiry_list | Enquiry Status, Approve/Decline Status is not available in API Response Date Format is not proper in API | Figma | FAIL | Enquiry Status, Approve/Decline Status | Enquiry Status, Approve/Decline Status as per Figma should include in API, Proper Date Format needs to apply in response | https://drive.google.com/file/d/17nN7Ymt7-bVEpFscGE-GIcoQEUldn5MW/view?usp=drive_link |  |  | Customer - {{url}}api/v1/admin/get-customer-list - Edit/Update customer API pending
002 | Open | Metal Product API, Add, update, delete, edit error is displaying while run it | 2024-05-14 | API |  |  | https://drive.google.com/file/d/1WkQXYmeZ_Xm6dAdaa98iPCf6MnGiGuj1/view?usp=drive_link
Update_profile | POST | {{url}}api/v1/update_profile | Customer api - update profile - profile pic validation issue - When update profile without profile pic upload than error is displayed as "Undefined / Key " which needs to resolved and validation not needed as profile pic is not mandatory field as per figma | FAIL |  | "Undefined / Key " error should not display | https://drive.google.com/file/d/1fQ1u4iwO50gOaz6AjFgl0tCRfrREYEhW/view?usp=drive_link

## Headway (hidden)
Bug Report - Headway
Bug ID | Bug Description | Date | Bug Type | Expected Result | Actual Result | Priority | Issue Proof | Device/Browser | Developer Name | Bug Status | Developer Comments | Tester Comment
001 | In Headway Set notification api validation needs to set for blank input, invalid input id like 9999 validation needs to pop-up like "ID not found", "Please enter type", etc. | 2024-05-04 | api-functional | Validation needs to set | Validations are missing | High | https://drive.google.com/file/d/1vkcRiU10bw7SO8U1dGpQ_bSy8ByA-why/view?usp=drive_link | Postman | Rakesh Singh | Open
001 | In Event and Event Member List Coding error is getting displayed as "attempt to read property "title" on null" Validation needs to set like "Event has not been initiate yet" | 2024-04-23 | Admin side issue | In Event Member List Coding error is getting displayed as "attempt to read property "title" on null" Validation needs to set like "Event has not been initiate yet" | In Event Member List Coding error is getting displayed as "attempt to read property "title" on null" Validation needs to set like "Event has not been initiate yet" | Medium | https://drive.google.com/file/d/1QsNUCTVCCQuSvwnj94UlF3cBLI1vNPk2/view?usp=drive_link | Low | Rakesh Singh | Open
002 | In CMS Pages while User Click on Edit and Update than In Success message spelling "updataed " s/b "updated" needs to correct Same spelling Issue in Blog Page and About Startup page | 2024-04-23 | Admin side issue | In CMS Pages while User Click on Edit and Update than In Success message spelling "updataed " s/b "updated" needs to correct | In CMS Pages while User Click on Edit and Update than In Success message spelling "updataed " s/b "updated" needs to correct | Medium | https://drive.google.com/file/d/1yuyCiVh1USliJIDF-copPL1-GsgSaOke/view?usp=drive_link | Low | Rakesh Singh | Open
003 | In CMS Pages Horizontal table should be Vertical scrollable table for easyness of admin user | 2024-04-23 | Admin side issue | In CMS Pages Horizontal table should be Vertical scrollable table for easyness of admin user | In CMS Pages Horizontal table should be Vertical scrollable table for easyness of admin user | Medium | https://drive.google.com/file/d/1-tn20wnVk5UTA0MYS-cxEO6CMNT4hCqw/view?usp=drive_link | Medium | Rakesh Singh | Open
004 | Contact Us table should be displayed in Admin side where Inquiry data Store Admin side | 2024-04-23 | Admin side issue | While User Do the Contact us from front side than Contact Us table should be available in Admin side where Inquiry detail should available Note :- Missing | While User Do the Contact us from front side than Contact Us table should be available in Admin side where Inquiry detail should available Note :- Missing | High |  |  | Rakesh Singh | Open
005 | In Admin side Registered users should be displayed which is missing | 2024-04-23 | Admin side issue | In Admin side Registered users should be displayed which is missing | In Admin side Registered users should be displayed which is missing | High |  |  | Rakesh Singh | Open
006 | Resend - Otp API is not working for headway website, it displayed error | 2024-05-03 | Admin side issue | While User hit the API with mobile number than Otp needs to regenerate | Reflecting an error while user hit the Resend OTP | High | https://drive.google.com/file/d/1ufTDz6l9tRYUmTFFb6wmjU_EzSyjvfrF/view?usp=drive_link |  | Rakesh Singh | Open
007 | In Admin Login Page Password needs to set eye icon for display password | 2024-05-09 | Admin side issue | Admin side eye icon needs to displayed for show password | Currently eye icon button for show password is missing | Medium | https://drive.google.com/file/d/1kR584nEs3JDTP3xcxASHYiVTtozCcxwQ/view?usp=drive_link |  | Rakesh Singh | Open
009 | Profile button is not responding it should be displayed admin information | 2024-05-09 | Admin side issue | Profile button is not responding it should be displayed admin information | Profile button is not responding it should be displayed admin information | Medium | https://drive.google.com/file/d/1BhY5L7QgsN35gmrjBOOJvZL0i14pK62w/view?usp=drive_link |  | Rakesh Singh | Open
As Discussed with Rakesh Sir below API's ready for test
| Seller Side | Status | Issue descriptions
| Add Products | Working | Missing validations when Remove product name, selling_price, price, etc. and send the requests than displayed Internal server error getting displayed instead of that respective validation messages can be displayed like " Product name should not blank", etc.
| Delete Products | Working
| Disable customer | Working
| Get Profile | Working
| Product list | Working
| Disable customer | Working
| Category List | Working
Admin Side
| Get Profile | Working
| Seller Detail | Working
| Customer list | Working
| Disable customer | Working

## Performance Observation (hidden)
013 | In Mobile Meet our team Scrolling down the page than for open the photos slowness observed | Meet Our Team | 2024-05-02 | Functional | 1. Meet our team

## minor (hidden)
004 | In Customer Support section under the privacy policy as per the content file there is a bullet point given which is missing | Privacy Policy | 2024-05-02 | Functional | 1. Go to Privacy Policy 2. scroll down | In Customer Support section under the privacy policy as per the content file there is a bullet point given which is missing | In Customer Support section under the privacy policy as per the content file there is a bullet point given which is missing | High | https://drive.google.com/file/d/1xSxaD3bh9iXUjyTWQX4ikZYavtwtULLv/view?usp=drive_link | Chrome | Kalpana | Open

## Other issues (hidden)
2024-04-23
1 | In Plan Pricing When Click on Book Now and when click on Proceed Now button than it is not responding Note :- Still issue is facing in new build | 1.Plan Pricing | 2024-04-23 | Functional | 1.Plan Pricing 2.Proceed now button click | In Plan Pricing while inspecing the console than API keys getting displayed in console , needs to fix this issue as a high priority | In Plan Pricing while inspecing the console than API keys getting displayed in console , needs to fix this issue as a high priority | Very High | https://drive.google.com/file/d/1fSXevleSj_DtIjiaZzFgqB16DUnlo1dx/view?usp=drive_link | Chrome | Kalpana Rajput | Open
2 | When user open the Home page than Home page is not constantly opening smoothly banner is taking load and displayed white space | 1. HomePage | 2024-04-23 | Functional -Performance |  | When user open the Home page than Home page is not constantly opening smoothly banner is taking load and displayed white space | When user open the Home page than Home page is not constantly opening smoothly banner is taking load and displayed white space | High | https://drive.google.com/file/d/12t29z6MFN399RVViSlNRjzr9r699biKK/view?usp=drive_link | Chrome | Kalpana Rajput | Open
5 | In Meet Our Team While User load the page from mobile than latency issue observed photo not smoothly loaded | 1. Meet Our Team | 2024-04-23 | Functional | 1. Meet Our Team | In Meet Our Team While User load the page from mobile than latency issue observed photo not smoothly loaded | In Meet Our Team While User load the page from mobile than latency issue observed photo not smoothly loaded | Medium |  |  | Kalpana Rajput | Open
6 | In Home Page Meet our Team Button is missing alignment in mobile device Real Me C53, Issue occurred while Retest new build | 1.Home | 2024-04-23 | Design | 1. Home | In Home Page Meet our Team Button is missing alignment | In Home Page Meet our Team Button is missing alignment | Medium | https://drive.google.com/file/d/17FG6eNkm9C1ugsl9xbqy14KNgc33DOhN/view?usp=drive_link |  | Kalpana Rajput | Open
7 | On HomePage "Shriji Jewellers', "N.K. Jewellers", etc. displayed in small size Note :- Still facing this in new build | 1.Home | 2024-04-23 | Design | 1. Home | On HomePage "Shriji Jewellers', "N.K. Jewellers", etc. displayed in small size | On HomePage "Shriji Jewellers', "N.K. Jewellers", etc. displayed in small size | Medium | https://drive.google.com/file/d/1fnhPT6zqn3nhMQjlWGJmEgNKXgPrAOvq/view?usp=drive_link | Mobile device | Kalpana Rajput | Open
8 | In Headway Initiatives Below SSU Slide show images are slightly jerking needs to resolved latency issue | 1.Headway Initiatives | 2024-04-23 | Functional | 1.Headway Initiatives | In Headway Initiatives Below SSU Slide show images are slightly jerking needs to resolved latency issue | In Headway Initiatives Below SSU Slide show images are slightly jerking needs to resolved latency issue | High | https://drive.google.com/file/d/1sRWQvdj76kMPJ0QWMMnJ8XWmXcZQrrLY/view?usp=drive_link | Mobile device | Kalpana Rajput | Open
11 | After the Done Payment user needs to received the Email notification
12